## Read me
The Capacity Model
Instrument 02 · juan.co/playbooks · © Juan.co LLC · Free to use with attribution.
One sheet per team, one tab per month. People across the top, projects down the side. Five rows do the work:
RATE — target utilization: the share of an eight-hour day the person is expected to deliver (0.8 for a maker, 0.5 for a manager). Input.
HOURS — working days × 8 × rate. The hours this person can give the book this month.
PTO — paid time off this month, in hours. Input.
ALLOC — hours minus PTO. What there is to assign.
USED — the sum of the project rows beneath. What has been assigned.
AVAIL — alloc minus used. Hours still free. A negative number is the point of the model: it is the deficit you did not know you had.
Blue cells are inputs. Black cells are formulas; leave them alone. The yellow cell is the month's working days.
"Example — June" is filled with a sample team of eight and ten projects, and it lands over-allocated on purpose. "Month" is blank: copy it once per month, name it, and fill it.
Column A totals the team: ALLOC, USED and AVAIL across everyone.
Pair this with The Project Budget (Instrument 03): the hours in a project's budget are the hours in that project's row here.
Sample names, projects and hours are invented. Rates of 0.5–0.8 are the ones I used; set yours.

## Example — June
Delivery team — example | PERSON | Avery | Blake | Casey | Devin | Emerson | Finley | Harper | Jordan
Working days in June | RATE | 0.5 | 0.8 | 0.8 | 0.8 | 0.8 | 0.5 | 0.8 | 0.7
22 | HOURS | 88 | 140.8 | 140.8 | 140.8 | 140.8 | 88 | 140.8 | 123.2
| PTO | 0 | 16 | 0 | 8 | 0 | 0 | 24 | 0
955.2 | ALLOC | 88 | 124.8 | 140.8 | 132.8 | 140.8 | 88 | 116.8 | 123.2
898 | USED | 68 | 148 | 148 | 148 | 138 | 62 | 78 | 108
57.2 | AVAIL | 20 | -23.2 | -7.2 | -15.2 | 2.8 | 26 | 38.8 | 15.2
PROJECT | HOURS
Harbor Logistics — platform migration | 100 | 20 | 40 | 40
Meridian Health — onboarding | 90 |  | 30 |  | 60
Atlas Retail — integration | 120 |  |  | 40 | 20 | 60
Summit Energy — renewal workshop | 40 | 16 |  |  |  |  | 24
Beacon Financial — reporting build | 104 |  | 24 |  | 40 | 40
Orchard Foods — data cleanup | 60 |  |  | 30 |  |  |  | 30
Pioneer Media — training | 110 | [5 empty] | 30 | 40 | 40
Keystone Legal — escalation support | 100 | 24 | 16 | [5 empty] | 60
Harbor Logistics — phase two | 110 |  | 30 | 30 | 20 | 30
Internal — process documentation | 64 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Note on A3: Working days in the month. Input.
Note on C2: Target utilization: the share of an 8-hour day this person is expected to bill or deliver. 0.8 for a maker, 0.5 for a manager. Input.
Note on C4: Paid time off this month, in hours. Input.
Note on C7: Hours left to assign. Negative means over-allocated — the number the model exists to show.

## Month
Team name | PERSON | Person 1 | Person 2 | Person 3 | Person 4 | Person 5 | Person 6 | Person 7 | Person 8
Working days in the month | RATE | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8
22 | HOURS | 140.8 | 140.8 | 140.8 | 140.8 | 140.8 | 140.8 | 140.8 | 140.8
PTO
1126.4 | ALLOC | 140.8 | 140.8 | 140.8 | 140.8 | 140.8 | 140.8 | 140.8 | 140.8
0 | USED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1126.4 | AVAIL | 140.8 | 140.8 | 140.8 | 140.8 | 140.8 | 140.8 | 140.8 | 140.8
PROJECT | HOURS
0
0
0
0
0
0
0
0
0
0
0
0
Note on A3: Working days in the month. Input.
Note on C2: Target utilization: the share of an 8-hour day this person is expected to bill or deliver. 0.8 for a maker, 0.5 for a manager. Input.
Note on C4: Paid time off this month, in hours. Input.
Note on C7: Hours left to assign. Negative means over-allocated — the number the model exists to show.