## Read me
The Project Budget
Instrument 03 · juan.co/playbooks · © Juan.co LLC · Free to use with attribution.
Four faces of one grid. Roles is the rate card. Budget is the plan: hours by role by month, priced at cost and at rate, with a margin. Track is the run: hours actually spent, and what is left. Performance is the verdict: plan against actuals, and the margin you really made.
Blue cells are inputs. Black cells are formulas. Green cells pull from another sheet. The yellow cells are the two levers: the loaded-cost multiplier and the margin floor on the Roles sheet.
Start on Roles: salaries, loaded-cost multiplier, target rates. Then Budget: name the project, set hours by role by month, add expenses. Track is filled as the work happens — hours actually spent, expenses actually incurred. Performance needs nothing typed.
The rule: no project is priced without a Budget, and no Budget is accepted below the margin floor. Change orders are new hours in Budget, dated, and the margin moves with them — or they are logged and the margin impact is recognised.
Pair this with The Capacity Model (Instrument 02): the hours in this Budget are the hours in the project's row there.
Sample roles, salaries, rates, hours and expenses are invented and rounded. The 1.8 loaded-cost multiplier and the 64% margin floor are the ones in the 2025 tool; the floor I ran an agency on was 73% for non-profit clients and higher for corporate. Set yours.

## Roles
Loaded-cost multiplier | 1.8
Margin floor | 64%
Hours in a working year | 2080
Role | Annual salary | Hourly salary | Loaded annual cost | Hourly cost | Target rate | Margin on salary | Margin on loaded cost | Rate to hit the floor
Principal | 200000 | 96.1538 | 360000 | 173.0769 | 485 | 80.17% | 64.31% | 480.7692
Engagement Manager | 150000 | 72.1154 | 270000 | 129.8077 | 365 | 80.24% | 64.44% | 360.5769
Senior Consultant | 130000 | 62.5 | 234000 | 112.5 | 315 | 80.16% | 64.29% | 312.5
Consultant | 100000 | 48.0769 | 180000 | 86.5385 | 245 | 80.38% | 64.68% | 240.3846
Project Manager | 110000 | 52.8846 | 198000 | 95.1923 | 265 | 80.04% | 64.08% | 264.4231
Designer | 95000 | 45.6731 | 171000 | 82.2115 | 230 | 80.14% | 64.26% | 228.3654
Developer | 120000 | 57.6923 | 216000 | 103.8462 | 290 | 80.11% | 64.19% | 288.4615
Analyst | 70000 | 33.6538 | 126000 | 60.5769 | 170 | 80.2% | 64.37% | 168.2692
Contractor (external) |  |  |  | 60 | 170 |  | 64.71% | 166.6667
Note on B1: Salary × this = what a person really costs (benefits, tools, seat, overhead). 1.8 is a defensible default for a services firm. Input.
Note on B2: No budget is accepted below this margin on loaded cost. Input.
Note on E14: A contractor has no salary: enter the hourly cost directly.
Note on I6: The rate that delivers the margin floor on loaded cost: hourly cost ÷ (1 − floor). If the target rate is below this, the role loses money at the floor.

## Budget
Project | Cost | Sale | Margin
Brand platform — 0001 | 112067.3077 | 314480 | 64.36%
Client
Acme Corporation
Floor | 64%
Hours | 1152
Expenses (sale) | 14820
Total sale incl. expenses | 329300
Role | Hourly cost | Rate | Hours | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Budget cost | Budget sale
Principal | 173.0769 | 485 | 20 | Jan: 8; Feb: 4; Mar: 4; Apr: 2; May: 2 | 3461.5385 | 9700
Engagement Manager | 129.8077 | 365 | 72 | Jan: 16; Feb: 16; Mar: 16; Apr: 16; May: 8 | 9346.1538 | 26280
Senior Consultant | 112.5 | 315 | 220 | Jan: 40; Feb: 60; Mar: 60; Apr: 40; May: 20 | 24750 | 69300
Consultant | 86.5385 | 245 | 320 | Jan: 40; Feb: 80; Mar: 80; Apr: 80; May: 40 | 27692.3077 | 78400
Project Manager | 95.1923 | 265 | 80 | Jan: 16; Feb: 16; Mar: 16; Apr: 16; May: 16 | 7615.3846 | 21200
Designer | 82.2115 | 230 | 100 | Jan: 0; Feb: 40; Mar: 40; Apr: 20; May: 0 | 8221.1538 | 23000
Developer | 103.8462 | 290 | 240 | Jan: 0; Feb: 40; Mar: 80; Apr: 80; May: 40 | 24923.0769 | 69600
Analyst | 60.5769 | 170 | 100 | Jan: 20; Feb: 20; Mar: 20; Apr: 20; May: 20 | 6057.6923 | 17000
Contractor (external) | 60 | 170 | 0 | [12 empty] | 0 | 0
|  |  | 0 | [12 empty] | 0 | 0
|  |  | 0 | [12 empty] | 0 | 0
|  |  | 0 | [12 empty] | 0 | 0
|  |  | 0 | [12 empty] | 0 | 0
|  |  | 0 | [12 empty] | 0 | 0
|  |  | 0 | [12 empty] | 0 | 0
|  |  | 0 | [12 empty] | 0 | 0
|  |  | 0 | [12 empty] | 0 | 0
|  |  | 0 | [12 empty] | 0 | 0
|  |  | 0 | [12 empty] | 0 | 0
|  |  | 0 | [12 empty] | 0 | 0
Totals |  |  | 1152 | 140 | 276 | 316 | 274 | 146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112067.3077 | 314480
Change orders
Date | Description | Hours added | Role | Jan: Approved by
Log every change order here, then add its hours to the role rows above, dated by month. A change order that is not in the grid is margin you gave away.
Note on D2: Margin on loaded cost. Turns coral when the budget is below the floor on the Roles sheet.

## Expenses
Category | Item | Est. qty | Est. unit cost | Est. total | Actual qty | Actual unit cost | Actual total | Remaining
Pre-production | Discovery travel | 2 | 800 | 1600 | 2 | 800 | 1600 | 0
Pre-production | Workshops and facilitation | 2 | 1500 | 3000 | 2 | 1500 | 3000 | 0
Travel | Airfare | 6 | 450 | 2700 | 6 | 450 | 2700 | 0
Travel | Hotels | 12 | 220 | 2640 | 14 | 220 | 3080 | -440
Travel | Ground and meals | 12 | 90 | 1080 | 14 | 90 | 1260 | -180
Software | Licences and environments | 5 | 400 | 2000 | 5 | 400 | 2000 | 0
Delivery | Printing and materials | 1 | 600 | 600 | 1 | 600 | 600 | 0
Delivery | Hand-off and documentation | 1 | 1200 | 1200 | 1 | 1200 | 1200 | 0
|  |  |  | 0 |  |  | 0 | 0
|  |  |  | 0 |  |  | 0 | 0
|  |  |  | 0 |  |  | 0 | 0
Totals |  |  |  | 14820 |  |  | 15440 | -620
Expenses are passed through at cost unless your contract marks them up; they sit outside the margin calculation and inside the invoice.
Note on G2: Defaults to the estimate; overwrite with the real unit cost when the invoice arrives.

## Track
Project | Run cost | Run sale | Run margin
Brand platform — 0001 | 120098.0769 | 336990 | 64.36%
Client
Acme Corporation
Hours budgeted | 1152
Hours spent | 1230
Hours remaining | -78
Expenses remaining | -620
Role | Budget hours | Remaining | Spent | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Run cost | Run sale
Principal | 20 | -4 | 24 | Jan: 8; Feb: 6; Mar: 4; Apr: 4; May: 2 | 4153.8462 | 11640
Engagement Manager | 72 | -2 | 74 | Jan: 16; Feb: 18; Mar: 16; Apr: 16; May: 8 | 9605.7692 | 27010
Senior Consultant | 220 | -20 | 240 | Jan: 44; Feb: 64; Mar: 60; Apr: 48; May: 24 | 27000 | 75600
Consultant | 320 | -16 | 336 | Jan: 40; Feb: 84; Mar: 88; Apr: 80; May: 44 | 29076.9231 | 82320
Project Manager | 80 | -4 | 84 | Jan: 16; Feb: 16; Mar: 20; Apr: 16; May: 16 | 7996.1538 | 22260
Designer | 100 | -4 | 104 | Jan: 0; Feb: 36; Mar: 48; Apr: 20; May: 0 | 8550 | 23920
Developer | 240 | -24 | 264 | Jan: 0; Feb: 40; Mar: 96; Apr: 88; May: 40 | 27415.3846 | 76560
Analyst | 100 | -4 | 104 | Jan: 20; Feb: 24; Mar: 20; Apr: 20; May: 20 | 6300 | 17680
Contractor (external) | 0 | 0 | 0 | [12 empty] | 0 | 0
0 | 0 | 0 | 0 | [12 empty] | 0 | 0
0 | 0 | 0 | 0 | [12 empty] | 0 | 0
0 | 0 | 0 | 0 | [12 empty] | 0 | 0
0 | 0 | 0 | 0 | [12 empty] | 0 | 0
0 | 0 | 0 | 0 | [12 empty] | 0 | 0
0 | 0 | 0 | 0 | [12 empty] | 0 | 0
0 | 0 | 0 | 0 | [12 empty] | 0 | 0
0 | 0 | 0 | 0 | [12 empty] | 0 | 0
0 | 0 | 0 | 0 | [12 empty] | 0 | 0
0 | 0 | 0 | 0 | [12 empty] | 0 | 0
0 | 0 | 0 | 0 | [12 empty] | 0 | 0
Totals | 1152 | -78 | 1230 | 144 | 288 | 352 | 292 | 154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120098.0769 | 336990
Note on E11: Hours actually spent, by role by month, from timesheets. Input — the only thing typed on this sheet.

## Performance
Project | Actual cost | Sale (as budgeted) | Realized margin
Brand platform — 0001 | 120098.0769 | 314480 | 61.81%
Client
Acme Corporation
Budget margin | 64.36%
Margin moved | -2.554%
Actualization | 106.8%
Cost overrun | 8030.7692
Role | Plan hours | Actual hours | Delta | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Actual cost | Sale at rate
Principal | 20 | 24 | 4 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4153.8462 | 9700
Engagement Manager | 72 | 74 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9605.7692 | 26280
Senior Consultant | 220 | 240 | 20 | 4 | 4 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27000 | 69300
Consultant | 320 | 336 | 16 | 0 | 4 | 8 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29076.9231 | 78400
Project Manager | 80 | 84 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7996.1538 | 21200
Designer | 100 | 104 | 4 | 0 | -4 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8550 | 23000
Developer | 240 | 264 | 24 | 0 | 0 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27415.3846 | 69600
Analyst | 100 | 104 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6300 | 17000
Contractor (external) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Totals | 1152 | 1230 | 78 | 4 | 12 | 36 | 18 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120098.0769 | 314480
Nothing is typed on this sheet. A positive delta is hours the project consumed beyond plan: unbilled unless a change order covers them.
Note on B7: Hours actually worked ÷ hours planned. Above 100% the project ate hours it did not sell; below, you over-estimated or under-delivered. Either way, the next estimate learns from it.