## Read me
The Success Initiative — the tracker
Play 04 · juan.co/playbooks · © Juan.co LLC · Free to use with attribution.
One workbook per initiative. When an account’s problems pile up, Customer Success gathers everything open into one scoped, signed, time-boxed engagement and runs it to steady state in seven to thirty days. It ends when the customer confirms every challenge identified is resolved.
Scope — the page the customer signs. Fill the blue cells after the structured call, print it, and have both leads sign. Tracker — one row per item in scope, with a condition, an owner on each side and dated dispositions, newest first; reactive items carry the 1-3-7 clock. Close — the customer’s confirmation, the recap, the hand-back and the watch. Book — every initiative you run, one row each, and the four measures of the play.
The 1-3-7 standard, for every reactive item: One — acknowledge the same day. Three — within three business days, a touchpoint that consolidates the feedback and makes it actionable: the problem, the recommended solution, the timeline. Seven — within seven calendar days, a major update, or the complete resolution or action plan. The Tracker computes the due dates and marks each one met or missed.
Blue cells are inputs; black cells are computed. Conditions are Green, Yellow or Red: a condition never changes without a dated disposition, and moves to Green only when the customer agrees. The sample account and its items are invented.
Pairs with The Success Initiative manual (Play 04), The Customer Health Score (the trigger), The Customer Journey (moment 23, milestone 09) and the Operating Model (the four plays).

## Scope
Success Initiative — scope of work
One page, signed by both leads. It says what is in, who does what, and by when.
Account | Meridian Freight Co.
Tier | Shared
Opened (scope signed) | 2026-10-12
Trigger | Critical mass
Kind of exception | Difficulty
The challenge, as we agreed it | Nightly data sync failures, a stalled reporting project and a disputed invoice have left the operations team working around the product for three weeks.
The state that ends it, in the customer’s words | “Our dispatch reports run on their own every morning, the reporting project is live, and the invoice is settled.”
Target close (no later than) | 2026-11-11
Days allowed | 30
Customer lead (name, title) | Operations director
Our lead (name, title) | Customer Success Manager
Weekly call | Tuesdays, 10:00, 30 minutes
What we will do | Resolve every item in scope through its functional owner; hold every reactive item to 1-3-7; run the weekly call; report every change of condition in writing.
What we ask of you | Name one lead for decisions and escalations; give access and approvals within two business days; join the weekly call; tell us when something is resolved for you.
Items in scope | 6
Operating agreement | Both sides agree to take part through the named leads, to escalate and delegate promptly, and to give feedback and approvals in an agreed time.
Approved by
| Name | Title | Date
For the customer
For us
Note on A11: Thirty days from the signed scope is the ceiling. Shorten it if the scope allows; never extend it in silence — re-scope with a structured call.

## Tracker
No. | Item | Source | Opened | Reactive? | Priority | Status | Condition | Customer owner | Our owner | Our function | Acknowledged | One met? | Plan due | Plan delivered | Three met? | Seven due | Resolved or updated | Seven met? | Disposition (dated, newest first)
1 | Nightly data sync failing | Case | 2026-10-12 | Yes | High | Open | Red | IT lead | Support engineer | Support | 2026-10-12 | Yes | 2026-10-15 | 2026-10-14 | Yes | 2026-10-19 |  | No | 2026-10-14 — Root cause found in the connector; fix scheduled 10/16; Support to confirm by noon 10/17. 2026-10-12 — Acknowledged by phone and email; plan promised by 10/14.
2 | Sync errors in the audit log | Case | 2026-10-12 | Yes | Med | Closed | Green | IT lead | Support engineer | Support | 2026-10-12 | Yes | 2026-10-15 | 2026-10-14 | Yes | 2026-10-19 | 2026-10-14 | Yes | 2026-10-14 — Same root cause as item 1; closed into it with the customer’s agreement.
3 | Reporting project stalled | Project | 2026-10-12 | No | Med | Open | Yellow | Operations director | Project manager | Onboarding | [8 empty] | 2026-10-13 — Downgraded to Yellow: one-week delay. Will move to Green on the customer’s sign-off.
4 | Invoice disputed | Invoice | 2026-10-12 | Yes | Med | Closed | Green | Controller | Billing lead | Finance | 2026-10-12 | Yes | 2026-10-15 | 2026-10-13 | Yes | 2026-10-19 | 2026-10-16 | Yes | 2026-10-16 — Credit issued; the customer confirmed. Closed. 2026-10-13 — Credit agreed in principle; Finance to issue.
5 | Dispatch report timing out | Case | 2026-10-13 | Yes | High | Open | Red | Operations director | Support engineer | Support | 2026-10-13 | Yes | 2026-10-16 | 2026-10-17 | No | 2026-10-20 |  | No | 2026-10-17 — Plan delivered two days late; workaround offered (run at 6:00, not 7:00). 2026-10-13 — Acknowledged.
6 | User permissions after reorganization | Escalation | 2026-10-14 | Yes | Low | Open | Yellow | IT lead | Customer Success Manager | Success | 2026-10-14 | Yes | 2026-10-19 |  | No | 2026-10-21 |  | No | 2026-10-14 — Acknowledged; plan promised by 10/17.
| Items |  | 6
| Open · Red · Yellow |  | 4 · 2 · 2
| 1-3-7 kept (met ÷ due) |  | 66.67%
Formulas:
One met? = IF(OR([Reactive?]<>"Yes",[Opened]=""),"",IF([Acknowledged]="",IF(TODAY()>[Opened],"No",""),IF([Acknowledged]<=[Opened],"Yes","No")))
Plan due = IF(OR([Reactive?]<>"Yes",[Opened]=""),"",WORKDAY([Opened],3))
Three met? = IF([Plan due]="","",IF([Plan delivered]="",IF(TODAY()>[Plan due],"No",""),IF([Plan delivered]<=[Plan due],"Yes","No")))
Seven due = IF(OR([Reactive?]<>"Yes",[Opened]=""),"",[Opened]+7)
Seven met? = IF([Seven due]="","",IF([Resolved or updated]="",IF(TODAY()>[Seven due],"No",""),IF([Resolved or updated]<=[Seven due],"Yes","No")))
Note on H1: Green, Yellow or Red. Never change it without a dated disposition; move it to Green only when the customer agrees.
Note on M1: One — acknowledged the same day the item was opened. Computed; blank until due.
Note on N1: Three — three business days from the opening. Computed.
Note on Q1: Seven — seven calendar days from the opening: a major update, or the complete resolution or action plan. Computed.

## Close
The close
An initiative is done when the customer confirms resolution of every challenge identified — not when our last case closes.
Items not yet Green | 4
Ready to confirm? | Not yet — 4 item(s) not Green
Confirmed by (name, title)
Confirmed on
Days to steady state
Within thirty days?
Recap call held on
Handed back to the tier’s touch on
Health thirty days after the close
Recurred within ninety days?
What changes so it does not recur

## Book
The book — every initiative, and the four measures
One row per initiative you run. The measures below say whether the play is working; the best sign is that you need it less. The sample rows are invented.
Account | Tier | Trigger | Kind | Opened | Confirmed | Days to steady state | 1-3-7 kept | Recurred in 90 days? | Health 30 days after | Renewed?
Meridian Freight Co. | Shared | Critical mass | Difficulty | 2026-10-12 |  |  | 66.67%
Harbor Logistics | Dedicated | Executive escalation | Ambiguity | 2026-07-06 | 2026-08-03 | 28 | 92% | No | Green | Yes
Northside Dental Group | Shared | Operations Red | Difficulty | 2026-08-17 | 2026-09-04 | 18 | 100% | No | Green
Pier 9 Credit Union | Dedicated | Scheduled | Complexity | 2026-06-01 | 2026-07-10 | 39 | 78% | No | Yellow | Yes
Dockside Supply Co. | Shared | Critical mass | Difficulty | 2026-05-04 | 2026-05-22 | 18 | 85% | Yes | Red | No
Mesa Analytics | Digital | Critical mass | Difficulty | 2026-09-08 | 2026-09-17 | 9 | 100% | No | Green
The four measures
Initiatives run | 6
Closed | 5
The clock — 1-3-7 kept (average) | 86.94%
The pace — median days to steady state | 18
…closed within thirty days | 80%
The cure — not recurred within ninety days | 80%
The result — Green thirty days after | 60%
…and renewed, where the renewal has come | 66.67%